EOWE Workspace

KI-based All-in-One Workspace — Mini-ERP & E-Commerce

Technical Requirements, Sprint Plan & Developer Task Split

Document type:  Technical requirements & delivery plan (v1.0)

Prepared for:  Development team — Adea Piperku & Lum Meta

Owner:  Arbios Kastrati (Project Lead)

Client:  EOWE

Date:  16 July 2026

MVP window:  20 July 2026 – 9 October 2026 (6 × 2-week sprints)

Kick-off:  Monday, 20 July 2026

# Contents

Contents	1

1. Project Overview	1

1.1 Objectives	1

1.2 Delivery Approach	1

1.3 Technology Stack	1

2. Team & Responsibilities	1

3. Architecture & Cross-Cutting Requirements	1

3.1 Non-Functional Requirements	1

3.2 AI / Human-in-the-Loop Principle	1

4. Sprint Timeline (MVP)	1

4.1 Sprint-by-Sprint Breakdown	1

5. Detailed Technical Requirements by Module	1

Foundation & Platform (Sprint 1)	1

Module 1 — Event & Participant Management	1

Module 2 — Contracts & Finance	1

Module 4 — Marketing & Social Media	1

Module 5 — Partner, Sponsoring & Service-Provider CRM	1

Module 3 — E-Commerce, Logistics & Administration	1

Module 6 — Future Expansion (post-MVP)	1

6. Getting Started — Monday 20 July	1

6.1 Open Points to Confirm with EOWE	1

# 1. Project Overview

EOWE manages a growing number of open-water swimming events, participants and partners on manual processes and basic SharePoint storage. This project delivers a tailored, AI-assisted “Mini-ERP” plus an integrated e-commerce shop that digitises and automates all event-dependent and event-independent business cases in one platform — a single source of truth.

## 1.1 Objectives

- Replace redundant Excel lists and scattered file storage with one central, always-current database (single source of truth).

- Reduce recurring manual work for management (GF/Markus) through AI: payment matching, email drafting, size aggregation.

- Integrate proven external tools (Tiger Timing, RaceResult, Qonto, DATEV) bidirectionally instead of replacing them (API-first).

- Ship a usable MVP in ~2–3 months, then extend iteratively without re-architecting.

## 1.2 Delivery Approach

Method: Agile, 2-week sprints. Each sprint ends with a short review (1–2 h) with GF/Markus (human-in-the-loop sign-off). Change requests are scheduled into the next sprint.

MVP module order (agreed): M1 → M2 → M4 → M5 → M3 → M6 (post-MVP). Module 1 (Event & Participant Management) is the operational core and is built first.

## 1.3 Technology Stack

| Layer | Technology | Notes |
| --- | --- | --- |
| Frontend | React + TypeScript, React Query, React Hook Form + Zod | SPA app shell, reusable component library / design system. |
| Backend | NestJS (Node.js) + TypeScript, REST API | Modular services mirroring the ERP modules. |
| Database | PostgreSQL | Single relational store; migrations via Prisma/TypeORM. |
| Auth | JWT + refresh tokens, RBAC | Roles: Admin, Management (GF), Staff, Read-only. |
| Storage | S3-compatible object storage (+ SharePoint sync hook) | Course maps, contracts, photos, assets. |
| AI / ML | NLP (email parsing/drafting), matching algorithms, computer vision | Human-in-the-loop for all customer-facing output. |
| Integrations | Tiger Timing, RaceResult, Qonto, DATEV, Stripe/PSP | API-first, bidirectional where supported. |
| DevOps | Docker, CI/CD, staging + production, monitoring | Auto-deploy to staging on merge to main. |

# 2. Team & Responsibilities

The project is delivered by a two-person full-stack team. Ownership is split so each module has a clear primary developer, while the foundation, hardening and go-live are shared. Both developers review each other’s pull requests.

| Developer | Focus | Primary responsibilities |
| --- | --- | --- |
| Adea Piperku | Frontend / Full-stack lead | React app shell & design system, dashboards, e-commerce shop frontend, human-in-the-loop & reconciliation UIs, contracts UI, alert UI, size aggregation. |
| Lum Meta | Backend / Integrations lead | NestJS APIs & data model, Tiger Timing / RaceResult / Qonto / DATEV integrations, AI email intake & payment matching, computer-vision photo tagging, inventory & stock engine. |
| Adea + Lum | Shared | Repo & CI/CD, auth/RBAC, notification service, MVP hardening, go-live & handover, cross-cutting pairing. |

Capacity assumption: a 2-week sprint provides roughly 8–9 ideal engineering days per developer. Estimates below are ideal days; the sprint plan in section 4 keeps each developer within this envelope.

# 3. Architecture & Cross-Cutting Requirements

The system is modular: each module is an independently deployable feature area on a shared platform (auth, data model, storage, notifications). This enables iterative releases so the team can work with the system early.

## 3.1 Non-Functional Requirements

- Security: RBAC on every endpoint; passwords hashed (argon2/bcrypt); secrets in a vault; audit log on core entities; GDPR-compliant handling of participant data.

- Reliability: external integrations use retry + exponential backoff; failures are logged and surfaced, never silently dropped.

- Performance: list/dashboard views respond < 1.5 s for typical data volumes; long jobs (imports, CV tagging) run async.

- Maintainability: shared lint/format config, typed end-to-end, module boundaries enforced, unit tests on business logic.

- Observability: centralized logging + error monitoring (e.g. Sentry); health checks on all services.

- Data integrity: soft-delete + audit trail; migrations reversible; nightly backups in production.

## 3.2 AI / Human-in-the-Loop Principle

All AI output that reaches a customer (email replies, size recommendations) or the books (payment matches) is proposed by the system and approved by a human before it takes effect. The AI accelerates; the person decides. Low-confidence results are always routed for manual review.

# 4. Sprint Timeline (MVP)

Six two-week sprints from 20 July to 9 October 2026. M6 (subscriptions, AI course simulation) is prepared in the data model but scheduled after MVP.

| Sprint | Dates | Theme / Goal | Adea d | Lum d |
| --- | --- | --- | --- | --- |
| S1 | 20 Jul – 31 Jul | Foundation & Platform Repo, CI/CD, DB, Auth/RBAC, app shell, design system, core data model. Everything M1+ builds on. | 4.8 | 7.3 |
| S2 | 3 Aug – 14 Aug | M1 Core – Events & Participants Event/Series/Race CRUD, participant registry, document store, dashboard skeleton. | 7 | 6 |
| S3 | 17 Aug – 28 Aug | M1 Integrations & AI Tiger Timing + RaceResult APIs, real-time registration dashboard, AI email assistant (wetsuit), finisher-shirt aggregation, camps/foreign events. | 6.5 | 10 |
| S4 | 31 Aug – 11 Sep | M2 – Contracts & Finance + AI Matching Digital contracts, all-event ticketing & discounts, Qonto banking, AI payment matching, DATEV export. | 6.5 | 8.5 |
| S5 | 14 Sep – 25 Sep | M4 Marketing + M5 Partner/Sponsor CRM Campaign & budget planning, Grid Sports asset approval, sponsoring CRM, service-provider coordination, alert engine, AI photo tagging. | 6 | 7.5 |
| S6 | 28 Sep – 9 Oct | M3 – E-Commerce, Inventory & MVP Hardening Online/on-site shop, catalog, checkout & payment, returns, inventory & resource planning, auto-reorder, UAT & MVP go-live. | 6.5 | 8 |

## 4.1 Sprint-by-Sprint Breakdown

### S1 · 20 Jul – 31 Jul — Foundation & Platform

Repo, CI/CD, DB, Auth/RBAC, app shell, design system, core data model. Everything M1+ builds on.

| ID | Task | Owner | Prio | Days |
| --- | --- | --- | --- | --- |
| F-01 | Provision monorepo (frontend React+TS, backend NestJS+TS), shared ESLint/Prettier/tsconfig, commit conventions. | Adea+Lum | Must | 1.5 |
| F-02 | CI/CD pipeline: lint + unit tests + build on PR; auto-deploy to staging on merge to main. | Lum | Must | 1.5 |
| F-03 | Dockerized local stack (PostgreSQL, API, web) + .env.example + secrets handling. | Lum | Must | 1 |
| F-04 | PostgreSQL schema v1 + migration tooling (Prisma/TypeORM); core entities: Tenant, User, Role, Event, Participant, Product, Partner. | Lum | Must | 2 |
| F-05 | Authentication (email+password, JWT/refresh) and RBAC with roles: Admin, GF/Management, Staff, Read-only. | Lum | Must | 2 |
| F-06 | React app shell: routing, auth guard, layout (nav + module menu), design system (component library, theme, tokens). | Adea | Must | 2.5 |
| F-07 | Global data layer: API client, React Query setup, error/toast handling, form validation (Zod/React Hook Form). | Adea | Must | 1.5 |

### S2 · 3 Aug – 14 Aug — M1 Core – Events & Participants

Event/Series/Race CRUD, participant registry, document store, dashboard skeleton.

| ID | Task | Owner | Prio | Days |
| --- | --- | --- | --- | --- |
| F-08 | Audit log + soft-delete convention; centralized logging & error monitoring (e.g. Sentry). | Lum | Should | 1 |
| F-09 | File/object storage service (S3-compatible) with virus-safe upload, plus optional SharePoint sync hook. | Lum | Must | 1.5 |
| M1-01 | CRUD for Series, Events, Races, Distances, Age/Level categories (e.g. Alpen Open Water Cup). | Adea | Must | 2.5 |
| M1-02 | Event capacity & scheduling: slots, dates, venues, status (draft/published/closed). | Adea | Must | 1.5 |
| M1-03 | Participant registry: profile (name, DOB/age, height, weight, contact, emergency), event enrollments, history. | Lum | Must | 2.5 |
| M1-04 | Bulk import/normalization of participants (CSV) as fallback before Tiger Timing sync. | Lum | Should | 1 |
| M1-05 | Central store for course maps / technical buoy drawings, linked to Event/Race; versioning + SharePoint link. | Adea | Must | 1.5 |
| M1-06 | Management dashboard skeleton: KPI tiles (registrations, capacity, revenue) with placeholder data source. | Adea | Must | 1.5 |

### S3 · 17 Aug – 28 Aug — M1 Integrations & AI

Tiger Timing + RaceResult APIs, real-time registration dashboard, AI email assistant (wetsuit), finisher-shirt aggregation, camps/foreign events.

| ID | Task | Owner | Prio | Days |
| --- | --- | --- | --- | --- |
| M1-07 | Bidirectional API integration with Tiger Timing (Meldewesen): pull registrations, push/confirm entries. | Lum | Must | 3 |
| M1-08 | API integration with RaceResult (billing/rankings): pull results & rankings, reconcile to participants. | Lum | Must | 2.5 |
| M1-09 | Real-time registration dashboard aggregating external systems (Tiger Timing) for live capacity monitoring. | Adea | Must | 2 |
| M1-10 | AI email intake: parse participant emails, match to DB record, classify intent (wetsuit, org question). | Lum | Must | 2.5 |
| M1-11 | Wetsuit recommendation engine: from age/height/weight → suggested brand/size + live stock check; draft reply. | Lum | Must | 2 |
| M1-12 | Human-in-the-loop approval UI: GF reviews/edits AI draft, one-click send, plus reminder (Wiedervorlage) scheduling. | Adea | Must | 2 |
| M1-13 | Finisher-shirt / merchandise size aggregation auto-computed from participant enrollments per event. | Adea | Must | 1 |
| M1-14 | Management areas for foreign/third-party events and swim camps (hotel + training management). | Adea | Should | 1.5 |

### S4 · 31 Aug – 11 Sep — M2 – Contracts & Finance + AI Matching

Digital contracts, all-event ticketing & discounts, Qonto banking, AI payment matching, DATEV export.

| ID | Task | Owner | Prio | Days |
| --- | --- | --- | --- | --- |
| M2-01 | Contract templates + automated generation of participant contracts (liability, cancellation clauses). | Adea | Must | 2.5 |
| M2-02 | Contract lifecycle: status (draft/sent/signed), storage, retrieval, audit trail. | Lum | Should | 1 |
| M2-03 | All-Event ticket management with automated discount handling & pricing rules. | Adea | Must | 2.5 |
| M2-04 | Invoice/fee generation per participant with open-balance tracking. | Lum | Must | 1.5 |
| M2-05 | Qonto banking API integration: pull transactions (Zahlungseingänge) in near real time. | Lum | Must | 2 |
| M2-06 | AI payment matching: match Qonto incoming payments to open participant fees via intelligent algorithm. | Lum | Must | 2.5 |
| M2-07 | Reconciliation review UI: confirm/override AI matches, mark paid, handle partial/over-payments. | Adea | Must | 1.5 |
| M2-08 | DATEV export for tax advisor (bookings/receipts in DATEV-compatible format). | Lum | Must | 1.5 |

### S5 · 14 Sep – 25 Sep — M4 Marketing + M5 Partner/Sponsor CRM

Campaign & budget planning, Grid Sports asset approval, sponsoring CRM, service-provider coordination, alert engine, AI photo tagging.

| ID | Task | Owner | Prio | Days |
| --- | --- | --- | --- | --- |
| M4-01 | Campaign & budget planning: event marketing (posters) + add-ons (parties, meet&greets) with budget vs actual. | Adea | Must | 2 |
| M4-02 | Asset library + approval interface for agency 'Grid Sports' to submit Instagram content for central release. | Adea | Must | 2 |
| M4-03 | Computer-vision auto-tagging of event photos into categories (start, course, finish, award, individual athlete). | Lum | Should | 2.5 |
| M5-01 | CRM for stakeholders: sponsors, partners, service providers with contacts, agreements, value tracking. | Lum | Must | 2.5 |
| M5-02 | Service-provider planning & cost tracking for essential partners (e.g. Wasserwacht) per event. | Lum | Must | 1.5 |
| M5-03 | Automated alert system: warn before contract expiry & on outstanding sponsoring payments. | Adea | Must | 2 |
| M5-04 | Notification service (in-app + email) shared across modules (alerts, reminders, approvals). | Lum | Should | 1 |

### S6 · 28 Sep – 9 Oct — M3 – E-Commerce, Inventory & MVP Hardening

Online/on-site shop, catalog, checkout & payment, returns, inventory & resource planning, auto-reorder, UAT & MVP go-live.

| ID | Task | Owner | Prio | Days |
| --- | --- | --- | --- | --- |
| M3-01 | Product catalog for 50–100 merchandising/swim-gear articles: variants (size/color), price, stock, images. | Adea | Must | 2 |
| M3-02 | Customer-facing online shop: browse, cart, checkout with payment (Stripe/PSP). | Adea | Must | 3 |
| M3-03 | On-site (POS-style) sales capture at events, drawing from same inventory. | Lum | Should | 1.5 |
| M3-04 | Returns/refund management (Retourenmanagement) tied to orders and stock. | Lum | Should | 1.5 |
| M3-05 | Inventory & resource planning: org materials (buoys, Restubes), storage locations, fleet (vans/GF car). | Lum | Must | 2 |
| M3-06 | Cloud stock management with min-quantity thresholds + automatic reorder suggestions. | Lum | Must | 1.5 |
| M3-07 | MVP hardening: UAT with EOWE, bug-fix pass, performance & security review, documentation. | Adea+Lum | Must | 2 |
| M3-08 | MVP production deployment + go-live runbook + handover to EOWE key users. | Adea+Lum | Must | 1 |

# 5. Detailed Technical Requirements by Module

Each requirement below carries an ID (matching the spreadsheet backlog), owner, sprint, priority and acceptance criteria. “Done” means the acceptance criteria are demonstrably met on staging.

## Foundation & Platform (Sprint 1)

### Environment & DevOps

F-01  Provision monorepo (frontend React+TS, backend FastAPI), shared ESLint/Prettier/tsconfig, commit conventions.

Owner: Adea+Lum   Sprint: S1   Priority: Must   Est: 1.5 d   Depends on: -

Acceptance: Repo cloned & bootstrapped by both devs; `npm run dev` starts FE+BE locally; lint passes in CI.

F-02  CI/CD pipeline: lint + unit tests + build on PR; auto-deploy to staging on merge to main.

Owner: Lum   Sprint: S1   Priority: Must   Est: 1.5 d   Depends on: F-01

Acceptance: PR triggers pipeline; green build auto-deploys to staging URL; failing tests block merge.

F-03  Dockerized local stack (PostgreSQL, API, web) + .env.example + secrets handling.

Owner: Lum   Sprint: S1   Priority: Must   Est: 1 d   Depends on: F-01

Acceptance: `docker compose up` runs full stack; onboarding doc lets a new dev run it in <15 min.

### Data & Persistence

F-04  PostgreSQL schema v1 + migration tooling (Prisma/TypeORM); core entities: Tenant, User, Role, Event, Participant, Product, Partner.

Owner: Lum   Sprint: S1   Priority: Must   Est: 2 d   Depends on: F-03

Acceptance: Migrations run forward/back cleanly; ER diagram committed; seed script creates demo data.

### Security & Access

F-05  Authentication (email+password, JWT/refresh) and RBAC with roles: Admin, GF/Management, Staff, Read-only.

Owner: Lum   Sprint: S1   Priority: Must   Est: 2 d   Depends on: F-04

Acceptance: User can log in/out; protected routes enforce role; unauthorized returns 403; passwords hashed (bcrypt/argon2).

### UI Platform

F-06  React app shell: routing, auth guard, layout (nav + module menu), design system (component library, theme, tokens).

Owner: Adea   Sprint: S1   Priority: Must   Est: 2.5 d   Depends on: F-01

Acceptance: Authenticated shell renders module nav; reusable Button/Input/Table/Modal/Form components documented in Storybook.

F-07  Global data layer: API client, React Query setup, error/toast handling, form validation (Zod/React Hook Form).

Owner: Adea   Sprint: S1   Priority: Must   Est: 1.5 d   Depends on: F-06

Acceptance: One vertical slice (e.g. Users list) fetches from API with loading/error states and validated form submit.

### Cross-cutting

F-08  Audit log + soft-delete convention; centralized logging & error monitoring (e.g. Sentry).

Owner: Lum   Sprint: S2   Priority: Should   Est: 1 d   Depends on: F-04

Acceptance: Create/update/delete on core entities writes audit entries; unhandled errors surface in monitoring.

F-09  File/object storage service (S3-compatible) with virus-safe upload, plus optional SharePoint sync hook.

Owner: Lum   Sprint: S2   Priority: Must   Est: 1.5 d   Depends on: F-04

Acceptance: File upload/download works with signed URLs; metadata stored in DB; large files stream, not buffered.

## Module 1 — Event & Participant Management

### Competition & Series Mgmt

M1-01  CRUD for Series, Events, Races, Distances, Age/Level categories (e.g. Alpen Open Water Cup).

Owner: Adea   Sprint: S2   Priority: Must   Est: 2.5 d   Depends on: F-06

Acceptance: User creates a Series with nested Events → Races → Distances; validation prevents overlaps; list & detail views.

M1-02  Event capacity & scheduling: slots, dates, venues, status (draft/published/closed).

Owner: Adea   Sprint: S2   Priority: Must   Est: 1.5 d   Depends on: M1-01

Acceptance: Capacity per race enforced; publishing an event makes it visible to registration flow; overbooking blocked.

### Participant Management

M1-03  Participant registry: profile (name, DOB/age, height, weight, contact, emergency), event enrollments, history.

Owner: Lum   Sprint: S2   Priority: Must   Est: 2.5 d   Depends on: F-04

Acceptance: Participant can be created/edited/searched; enrollment links participant↔race; body metrics stored for AI use.

M1-04  Bulk import/normalization of participants (CSV) as fallback before Tiger Timing sync.

Owner: Lum   Sprint: S2   Priority: Should   Est: 1 d   Depends on: M1-03

Acceptance: CSV upload maps columns, validates, reports errors per row, dedupes by email/name+DOB.

### Document & Media Store

M1-05  Central store for course maps / technical buoy drawings, linked to Event/Race; versioning + SharePoint link.

Owner: Adea   Sprint: S2   Priority: Must   Est: 1.5 d   Depends on: F-09

Acceptance: Files attach to a race, are previewable, versioned, and searchable by event/type tag.

### Dashboard

M1-06  Management dashboard skeleton: KPI tiles (registrations, capacity, revenue) with placeholder data source.

Owner: Adea   Sprint: S2   Priority: Must   Est: 1.5 d   Depends on: M1-01

Acceptance: Dashboard route renders KPI tiles + per-event drill-down; layout responsive; data wired to real API in S3.

M1-09  Real-time registration dashboard aggregating external systems (Tiger Timing) for live capacity monitoring.

Owner: Adea   Sprint: S3   Priority: Must   Est: 2 d   Depends on: M1-07,M1-06

Acceptance: Dashboard shows live registration counts vs capacity per event; auto-refresh; export to CSV.

### Integration: Tiger Timing

M1-07  Bidirectional API integration with Tiger Timing (Meldewesen): pull registrations, push/confirm entries.

Owner: Lum   Sprint: S3   Priority: Must   Est: 3 d   Depends on: M1-03

Acceptance: Registrations sync into participant registry on schedule + on demand; conflicts logged; mapping documented; ret/backoff on failure.

### Integration: RaceResult

M1-08  API integration with RaceResult (billing/rankings): pull results & rankings, reconcile to participants.

Owner: Lum   Sprint: S3   Priority: Must   Est: 2.5 d   Depends on: M1-07

Acceptance: Results import per race; rankings visible in event detail; reconciliation flags unmatched entries.

### AI – Email Assistant (HITL)

M1-10  AI email intake: parse participant emails, match to DB record, classify intent (wetsuit, org question).

Owner: Lum   Sprint: S3   Priority: Must   Est: 2.5 d   Depends on: M1-03,F-09

Acceptance: Incoming email matched to participant by name; intent classified; low-confidence flagged for manual routing.

M1-11  Wetsuit recommendation engine: from age/height/weight → suggested brand/size + live stock check; draft reply.

Owner: Lum   Sprint: S3   Priority: Must   Est: 2 d   Depends on: M1-10,M3-06

Acceptance: Given metrics + stock, system proposes size (e.g. Arena M) with availability; generates draft mail; blocks if out of stock.

M1-12  Human-in-the-loop approval UI: GF reviews/edits AI draft, one-click send, plus reminder (Wiedervorlage) scheduling.

Owner: Adea   Sprint: S3   Priority: Must   Est: 2 d   Depends on: M1-11

Acceptance: GF sees draft + source data side-by-side; can edit & send; reminder mail scheduled (e.g. 1 day pre-race).

### AI – Aggregation

M1-13  Finisher-shirt / merchandise size aggregation auto-computed from participant enrollments per event.

Owner: Adea   Sprint: S3   Priority: Must   Est: 1 d   Depends on: M1-03

Acceptance: Per-event report totals shirt sizes in real time from registrations; exportable order list per size.

### Additional Events & Camps

M1-14  Management areas for foreign/third-party events and swim camps (hotel + training management).

Owner: Adea   Sprint: S3   Priority: Should   Est: 1.5 d   Depends on: M1-01

Acceptance: Camp entity supports hotel nights & training sessions; third-party events tracked separately from own events.

## Module 2 — Contracts & Finance

### Digital Contracts

M2-01  Contract templates + automated generation of participant contracts (liability, cancellation clauses).

Owner: Adea   Sprint: S4   Priority: Must   Est: 2.5 d   Depends on: M1-03

Acceptance: Template merges participant/event data into PDF; legally-safe archival with timestamp; downloadable & emailable.

M2-02  Contract lifecycle: status (draft/sent/signed), storage, retrieval, audit trail.

Owner: Lum   Sprint: S4   Priority: Should   Est: 1 d   Depends on: M2-01

Acceptance: Each contract has status + history; signed copies archived; searchable by participant/event.

### Ticketing & Billing

M2-03  All-Event ticket management with automated discount handling & pricing rules.

Owner: Adea   Sprint: S4   Priority: Must   Est: 2.5 d   Depends on: M1-01

Acceptance: Ticket types configurable; rule engine applies discounts; price shown pre/post-discount; combinable rules validated.

M2-04  Invoice/fee generation per participant with open-balance tracking.

Owner: Lum   Sprint: S4   Priority: Must   Est: 1.5 d   Depends on: M2-03

Acceptance: Fees generated per enrollment/ticket; open vs paid status tracked; invoice PDF produced.

### Integration: Qonto

M2-05  Qonto banking API integration: pull transactions (Zahlungseingänge) in near real time.

Owner: Lum   Sprint: S4   Priority: Must   Est: 2 d   Depends on: F-04

Acceptance: Bank transactions imported on schedule; stored with metadata; reconciliation-ready; secure credential storage.

### AI – Payment Matching

M2-06  AI payment matching: match Qonto incoming payments to open participant fees via intelligent algorithm.

Owner: Lum   Sprint: S4   Priority: Must   Est: 2.5 d   Depends on: M2-04,M2-05

Acceptance: Incoming payment auto-matched to open fee (amount/name/reference); confidence score; unmatched queued for review.

M2-07  Reconciliation review UI: confirm/override AI matches, mark paid, handle partial/over-payments.

Owner: Adea   Sprint: S4   Priority: Must   Est: 1.5 d   Depends on: M2-06

Acceptance: User sees suggested matches ranked; can confirm/reassign; balances update; partial payments supported.

### Accounting: DATEV

M2-08  DATEV export for tax advisor (bookings/receipts in DATEV-compatible format).

Owner: Lum   Sprint: S4   Priority: Must   Est: 1.5 d   Depends on: M2-04

Acceptance: Export generates valid DATEV CSV/format for a date range; reconciled entries included; downloadable.

## Module 4 — Marketing & Social Media

### Campaign Planning

M4-01  Campaign & budget planning: event marketing (posters) + add-ons (parties, meet&greets) with budget vs actual.

Owner: Adea   Sprint: S5   Priority: Must   Est: 2 d   Depends on: F-06

Acceptance: Create campaigns with budget lines; track planned vs actual spend; link campaigns to events.

### Asset Management

M4-02  Asset library + approval interface for agency 'Grid Sports' to submit Instagram content for central release.

Owner: Adea   Sprint: S5   Priority: Must   Est: 2 d   Depends on: F-09

Acceptance: Agency uploads assets; EOWE reviews/approves/rejects with comments; approved assets flagged ready-to-publish.

### AI – Photo Sorting

M4-03  Computer-vision auto-tagging of event photos into categories (start, course, finish, award, individual athlete).

Owner: Lum   Sprint: S5   Priority: Should   Est: 2.5 d   Depends on: F-09

Acceptance: Uploaded photos auto-tagged into configured categories; manual re-tag possible; batch upload supported.

## Module 5 — Partner, Sponsoring & Service-Provider CRM

### Sponsoring Management

M5-01  CRM for stakeholders: sponsors, partners, service providers with contacts, agreements, value tracking.

Owner: Lum   Sprint: S5   Priority: Must   Est: 2.5 d   Depends on: F-04

Acceptance: Partner records with type, contacts, linked events; monetary + in-kind (Sachleistungen) contributions logged.

### Service Provider Coordination

M5-02  Service-provider planning & cost tracking for essential partners (e.g. Wasserwacht) per event.

Owner: Lum   Sprint: S5   Priority: Must   Est: 1.5 d   Depends on: M5-01

Acceptance: Assign providers to events with planned/actual cost; availability & booking status tracked.

### Alert Engine

M5-03  Automated alert system: warn before contract expiry & on outstanding sponsoring payments.

Owner: Adea   Sprint: S5   Priority: Must   Est: 2 d   Depends on: M5-01

Acceptance: Rules trigger notifications X days before expiry / on overdue payment; alerts shown in-app + email; configurable thresholds.

M5-04  Notification service (in-app + email) shared across modules (alerts, reminders, approvals).

Owner: Lum   Sprint: S5   Priority: Should   Est: 1 d   Depends on: F-08

Acceptance: Central notification service delivers in-app + email; used by M1 reminders, M5 alerts; user preferences honored.

## Module 3 — E-Commerce, Logistics & Administration

### Product Catalog

M3-01  Product catalog for 50–100 merchandising/swim-gear articles: variants (size/color), price, stock, images.

Owner: Adea   Sprint: S6   Priority: Must   Est: 2 d   Depends on: F-06,M3-06

Acceptance: Products with variants CRUD; images; price & stock per variant; category filtering & search.

### Online Shop

M3-02  Customer-facing online shop: browse, cart, checkout with payment (Stripe/PSP).

Owner: Adea   Sprint: S6   Priority: Must   Est: 3 d   Depends on: M3-01

Acceptance: Customer adds to cart, checks out, pays; order created; stock decremented; confirmation email sent.

### On-site Sales

M3-03  On-site (POS-style) sales capture at events, drawing from same inventory.

Owner: Lum   Sprint: S6   Priority: Should   Est: 1.5 d   Depends on: M3-01

Acceptance: Staff records on-site sale; inventory updates in real time; sale linked to event & payment method.

### Returns

M3-04  Returns/refund management (Retourenmanagement) tied to orders and stock.

Owner: Lum   Sprint: S6   Priority: Should   Est: 1.5 d   Depends on: M3-02

Acceptance: Return initiated against an order; refund recorded; stock re-incremented; return status tracked.

### Inventory & Resources

M3-05  Inventory & resource planning: org materials (buoys, Restubes), storage locations, fleet (vans/GF car).

Owner: Lum   Sprint: S6   Priority: Must   Est: 2 d   Depends on: M3-01

Acceptance: Assets tracked with quantity, location, assignment to events; fleet bookable per event.

M3-06  Cloud stock management with min-quantity thresholds + automatic reorder suggestions.

Owner: Lum   Sprint: S6   Priority: Must   Est: 1.5 d   Depends on: M3-05

Acceptance: Stock below min triggers reorder suggestion; suggestion list exportable; feeds wetsuit stock check (M1-11).

### Hardening

M3-07  MVP hardening: UAT with EOWE, bug-fix pass, performance & security review, documentation.

Owner: Adea+Lum   Sprint: S6   Priority: Must   Est: 2 d   Depends on: M3-02

Acceptance: UAT checklist signed off; critical/high bugs closed; smoke tests pass on staging; user & admin docs delivered.

### Go-Live

M3-08  MVP production deployment + go-live runbook + handover to EOWE key users.

Owner: Adea+Lum   Sprint: S6   Priority: Must   Est: 1 d   Depends on: M3-07

Acceptance: Production env live; backups & monitoring active; rollback documented; key users onboarded.

## Module 6 — Future Expansion (post-MVP)

### Subscription Model

M6-01  Subscription management: recurring billing, digital+physical service packages (training videos, personalized gear).

Owner: Adea+Lum   Sprint: Backlog   Priority: Could   Est: 5 d   Depends on: M2-05

Acceptance: Deferred to post-MVP: recurring payment integration combinable with All-Event ticket. Data model prepared in MVP.

### AI – Course Simulation

M6-02  Geodata-based AI buoy-setting: simulate & propose new courses for additional age/level classes.

Owner: Adea+Lum   Sprint: Backlog   Priority: Could   Est: 8 d   Depends on: M1-05

Acceptance: Deferred (advanced): requires geodata processing; MVP only stores course maps/drawings centrally.

# 6. Getting Started — Monday 20 July

Sprint 1 is foundation work both developers do together so every later module has solid ground. Suggested order for the first two days:

- Both: clone the monorepo, agree branch/PR conventions, confirm everyone can run FE + BE locally (F-01).

- Lum: stand up Docker stack + PostgreSQL and the migration tooling; commit the v1 schema and ER diagram (F-03, F-04).

- Adea: scaffold the React app shell, routing and the first design-system components in Storybook (F-06).

- Lum: wire CI/CD so PRs run lint + tests and merges deploy to staging (F-02).

- Both: implement auth + RBAC end-to-end as the first vertical slice, then split into module work from Sprint 2 (F-05, F-07).

Definition of Done (every task): acceptance criteria met, code reviewed by the other developer, tests where applicable, deployed to staging, no open critical/high bugs.

## 6.1 Open Points to Confirm with EOWE

These do not block the start but should be clarified during Sprint 1–2 reviews:

- API credentials & documentation for Tiger Timing, RaceResult and Qonto (and DATEV export spec / advisor requirements).

- Payment service provider choice for the shop (Stripe assumed) and legal review of contract templates.

- Exact discount rules for All-Event tickets and the roster of merchandising SKUs (50–100).

- SharePoint integration depth (link vs full sync) for course maps and documents.